Implementation Plan

Web-Based Internet Radio Streaming System

| Project | Web-Based Internet Radio Streaming System |
| --- | --- |
| Document version | 1.0 |
| Prepared | 29 October 2026 |
| Status | Proposed baseline — confirm assumptions during implementation |

# 1. Plan Overview

This plan turns the project scope into an ordered implementation workflow. It prioritizes a working basic radio player first, then adds responsive polish, error handling, testing, documentation, and optional Icecast integration.

| Planning assumption | Baseline |
| --- | --- |
| Approach | Build the static frontend first; do not add a backend or database unless a requirement changes. |
| Technology | HTML5, CSS3, JavaScript, HTML5 Audio; optional Icecast and compatible broadcaster software. |
| Development tool | Visual Studio Code and a modern browser. |
| Schedule | Illustrative 3-week plan for one developer; adjust to internship deadlines and available stream access. |
| Completion rule | Do not mark a feature complete until it is tested and the result is recorded. |

# 2. Target Architecture

| Part | Implementation choice | Notes |
| --- | --- | --- |
| Frontend structure | index.html | Semantic page structure and audio element. |
| Styles | styles.css | Layout, typography, responsive breakpoints, focus states. |
| Player logic | script.js | Play/pause, volume, media events, status and errors. |
| Configuration | Config section in script.js or data attributes | Station name, description, and authorized stream URL. |
| Audio delivery | Existing authorized stream URL | Use this for the MVP. |
| Optional streaming | Icecast + broadcaster/source software | Only implement after the browser player works with a known-good stream. |
| Hosting | Static web host or local development server | Use HTTPS in deployment, especially if the stream is HTTPS-only. |

# 3. Recommended Project Structure

internet-radio/
├── index.html
├── css/
│   └── styles.css
├── js/
│   └── script.js
├── assets/
│   ├── logo.svg (optional)
│   └── station-artwork.jpg (optional)
├── tests/
│   └── test-checklist.md
└── README.md

Keep the initial project small. Do not create a backend, database, login system, or admin panel for the basic scope.

# 4. Phase-by-Phase Implementation

## Phase 1 — Confirm requirements and stream (Day 1)

Confirm the station name, description, branding, and whether the demo uses an existing stream or self-hosted Icecast.

Obtain a stream URL that the project is authorized to use.

Open the stream URL or a known-good player in target browsers and verify that audio can be heard.

Record stream format, HTTPS/HTTP, any redirects, and any restrictions provided by the stream owner.

Create a short README with the selected option and known limitations.

Exit criterion: a tested, authorized stream URL is available, or the Icecast option is explicitly selected.

## Phase 2 — Create the frontend skeleton (Days 2–3)

Create index.html, css/styles.css, js/script.js, and optional assets folders.

Use semantic HTML for page header, station details, player controls, status text, and footer.

Add an HTML5 audio element and connect the configured stream URL.

Add accessible labels and keyboard-visible focus states.

Create a basic responsive layout before adding decorative effects.

Exit criterion: page renders with station information and usable controls at desktop and mobile widths.

## Phase 3 — Implement playback controls (Days 4–5)

Add a Play button that calls audio.play() in response to a user action.

Handle the Promise returned by audio.play() and show a useful message if playback is rejected.

Add Pause/Resume behaviour using audio.pause() and the current paused state.

Add a volume slider mapped to audio.volume between 0 and 1.

Disable or adjust controls only when necessary; do not make the player unusable during loading.

Exit criterion: valid-stream play, pause, resume, and volume tests pass.

## Phase 4 — Status and error handling (Days 6–7)

Listen for relevant audio events such as loadstart, canplay, playing, pause, waiting, stalled, and error.

Map events to concise states: Ready, Loading, Playing, Paused, Buffering, and Stream Error.

Ensure event order does not leave a stale state after the user pauses or retries.

Provide a Retry action that attempts playback again after a user gesture.

Handle missing URL and unsupported/failed playback with clear messages.

Exit criterion: invalid, unavailable, and buffering cases produce understandable feedback.

## Phase 5 — Responsive design and accessibility (Days 8–9)

Test narrow phone, tablet, laptop, and desktop widths using browser developer tools.

Ensure buttons and sliders are large enough to use on touch screens.

Check contrast, font size, focus indicators, labels, and keyboard navigation.

Avoid autoplay with sound; require the listener to press Play.

Optimize images and avoid unnecessary JavaScript libraries or large assets.

Exit criterion: no critical usability issue remains on the tested viewports.

## Phase 6 — Optional Icecast integration (Days 10–12)

Skip this phase if the approved deliverable only requires an existing stream URL.

Choose a host or test machine that can run Icecast and be reached by listener devices.

Install and configure Icecast using its official documentation for the target operating system.

Configure the compatible broadcaster/source software and supply audio to the server.

Verify source connection, mount point, listener URL, authentication, port/firewall rules, and HTTPS/reverse-proxy needs.

Test the stream from another device and from outside the local network if remote listening is required.

Do not expose source credentials in frontend JavaScript or public repositories.

Exit criterion: at least two listener devices can play the stream within the test environment's capacity.

## Phase 7 — System testing and fixes (Days 13–14)

Run every SRS test case and record Pass/Fail, browser/device, date, and evidence.

Test with a valid URL, invalid URL, unavailable stream, and unstable connection where feasible.

Test volume, play/pause/resume, status updates, keyboard operation, and responsive layout.

Test the deployed HTTPS site and check browser console/network errors.

Fix defects and rerun the failed tests.

Exit criterion: all mandatory tests pass or remaining limitations are documented and approved.

## Phase 8 — Deployment and handover (Days 15–16)

Deploy the static frontend to the selected hosting environment or prepare a reproducible local demo.

Confirm the stream URL is still working from the deployed site.

Write README instructions for configuration, running locally, deployment, and troubleshooting.

Prepare screenshots and a short demonstration sequence.

Document known limitations and optional future enhancements.

Exit criterion: another person can run or access the application using the README.

# 5. Suggested 3-Week Schedule

| Week | Focus | Deliverable |
| --- | --- | --- |
| Week 1 | Requirements, stream validation, page structure, basic controls | Working MVP with play/pause and volume |
| Week 2 | Status/error handling, responsive styling, accessibility, optional Icecast setup | Feature-complete candidate |
| Week 3 | Testing, defect fixes, deployment, README, demo preparation | Tested and documented release |

The day estimates are planning estimates, not a guarantee. Icecast setup may take longer if hosting, network access, HTTPS, or broadcaster configuration is unfamiliar.

# 6. Detailed Development Tasks

| Task ID | Task | Priority | Depends on | Completion evidence |
| --- | --- | --- | --- | --- |
| IMP-01 | Confirm requirements and authorized stream | Must | None | Stream details recorded |
| IMP-02 | Build semantic HTML structure | Must | IMP-01 | Page loads in browser |
| IMP-03 | Implement responsive CSS | Must | IMP-02 | Desktop/mobile screenshots |
| IMP-04 | Connect HTML5 Audio to stream URL | Must | IMP-01, IMP-02 | Audio plays |
| IMP-05 | Implement play/pause/resume | Must | IMP-04 | Manual test result |
| IMP-06 | Implement volume control | Must | IMP-04 | Volume test result |
| IMP-07 | Implement media states and error handling | Must | IMP-04 | Error and buffering tests |
| IMP-08 | Accessibility and keyboard review | Must | IMP-03, IMP-05, IMP-06 | Checklist completed |
| IMP-09 | Cross-browser/device testing | Must | IMP-05 to IMP-08 | Test matrix completed |
| IMP-10 | Icecast setup and multi-listener test | Optional | MVP passes | Two-device test |
| IMP-11 | Deploy and verify HTTPS | Must for hosted release | MVP passes | Public/staging URL verified |
| IMP-12 | README and handover documentation | Must | Implementation complete | README reviewed |

# 7. Implementation Guidance

## 7.1 HTML responsibilities

Use a semantic heading for the station name and a paragraph for station details.

Use buttons for Play/Pause and Retry; use a labelled range input for volume.

Use a dedicated status element with an accessible live-region strategy for important status changes.

Keep the audio element controlled by JavaScript; do not assume autoplay will be permitted.

## 7.2 JavaScript responsibilities

Keep a single audio element and a small set of functions for play, pause, retry, volume, and status updates.

Use audio events as the source of truth for playback state where possible.

Handle the rejection of audio.play() rather than assuming playback started.

Avoid updating the interface to Playing until the browser reports actual playback.

Do not expose passwords, source credentials, or private server configuration in client-side code.

## 7.3 CSS responsibilities

Use a mobile-first layout with flexible widths and sensible spacing.

Make the main play control visually obvious without sacrificing contrast or focus visibility.

Use responsive sizing for station artwork and controls.

Respect reduced-motion preferences if animations are added.

# 8. Testing Checklist

☐ Page opens without uncaught JavaScript errors.

☐ Station name and description match the configuration.

☐ Play starts the configured compatible stream after a user action.

☐ Pause stops playback; resume attempts playback again.

☐ Volume slider changes the audio volume.

☐ Ready/loading/playing/paused/buffering/error messages are accurate.

☐ Invalid or unavailable URL does not crash the page.

☐ Retry works after the stream becomes available.

☐ Keyboard navigation and focus indicators work.

☐ Layout remains usable on narrow and wide viewports.

☐ No avoidable HTTPS mixed-content errors occur.

☐ Optional Icecast stream works from two listener devices.

☐ README steps have been tested by following them from a clean start.

# 9. Risks and Troubleshooting

| Symptom | Likely cause | Action |
| --- | --- | --- |
| Play button does nothing | JavaScript error, wrong element ID, or rejected play() Promise | Check browser console; handle Promise rejection; verify element references. |
| Audio cannot load | Invalid URL, stream offline, unsupported format, or redirect issue | Open the endpoint in a known-good player; inspect Network panel and server status. |
| Works locally but not after deployment | HTTPS mixed content, CORS/redirect behaviour, or host restrictions | Use a compatible HTTPS endpoint and inspect console/network requests. |
| Works on one browser only | Codec or browser support differences | Test target browsers and choose a supported stream format. |
| Icecast works on same machine only | Bound address, firewall, router, or private LAN address | Check server binding, ports, firewall, and whether the listener URL is externally reachable. |
| Status remains stuck | Media events are not mapped consistently | Review event listeners and ensure pause/error events override stale status. |

# 10. Deployment and Handover

Choose a static hosting provider or documented local demonstration environment.

Upload the HTML, CSS, JavaScript, and licensed assets.

Set the final authorized stream URL and station metadata.

Verify that the website and stream are reachable with compatible security protocols.

Run the core acceptance tests against the deployed version.

Provide README instructions, test results, screenshots, and a list of limitations.

# 11. Final Deliverables

Source code organized into HTML, CSS, and JavaScript files.

Working radio player with play/pause, volume, status, and error feedback.

Responsive desktop/mobile interface.

Optional Icecast configuration notes and multi-listener test evidence.

Test checklist with actual results.

README with setup, configuration, deployment, and troubleshooting.

Short demo script and known-limitations section.

# 12. Demo Sequence

Open the deployed website and introduce the station name.

Press Play and confirm the Playing status and audible stream.

Adjust the volume.

Pause and resume playback.

Briefly show the responsive layout at a mobile viewport.

If available, demonstrate a controlled error/retry case.

If Icecast was implemented, show the stream playing on a second device.

# 13. Definition of Done

All must-have SRS requirements are implemented.

Core playback controls work with the selected valid stream.

Errors are handled with clear user feedback.

Responsive and keyboard-accessibility checks are complete.

Mandatory tests are passed or exceptions are explicitly documented.

Deployment/run instructions are reproducible.

No unapproved out-of-scope features have been added at the expense of core reliability.