Implementation Plan

Full-Stack Internet Radio Streaming System

| Project | Full-Stack Internet Radio Streaming System |
| --- | --- |
| Version | 2.0 — Backend-enabled scope |
| Prepared | 29 October 2026 |
| Status | Proposed specification; confirm stream and deployment choices before coding |

# 1. Implementation strategy

Build in vertical slices: first make the player work with a known-good stream, then add Express and MySQL, then connect the frontend to the API, and finally implement authentication/admin workflows, testing and deployment. Do not start with Icecast; add it only after the browser player works with an existing authorized stream.

| Decision | Recommendation |
| --- | --- |
| Frontend | HTML5, CSS3, vanilla JavaScript |
| Backend | Node.js + Express |
| Database | MySQL |
| Database driver | mysql2 with parameterized queries |
| Authentication | bcrypt password hashing and JWT in HttpOnly cookie or a server-side session; choose one and implement consistently |
| Validation | Use a validation library or explicit schema validation for every API input |
| Audio | HTML5 Audio plays the configured stream directly |
| Optional stream server | Icecast, only after MVP is working |
| Testing | Postman/Insomnia or equivalent plus browser checks and SQL verification |

# 2. Repository structure

internet-radio/
├── frontend/
│   ├── index.html
│   ├── stations.html
│   ├── station.html
│   ├── login.html
│   ├── register.html
│   ├── favourites.html
│   ├── admin/
│   │   ├── stations.html
│   │   └── schedules.html
│   ├── css/styles.css
│   ├── js/
│   │   ├── api.js
│   │   ├── player.js
│   │   ├── auth.js
│   │   ├── stations.js
│   │   └── admin.js
│   └── assets/
├── backend/
│   ├── src/
│   │   ├── app.js
│   │   ├── server.js
│   │   ├── config/db.js
│   │   ├── routes/
│   │   ├── controllers/
│   │   ├── services/
│   │   ├── middleware/auth.js
│   │   ├── middleware/errorHandler.js
│   │   ├── validators/
│   │   └── utils/
│   ├── sql/schema.sql
│   ├── .env.example
│   └── package.json
├── tests/
│   ├── api-test-checklist.md
│   └── manual-test-checklist.md
└── README.md

Keep frontend and backend responsibilities separate. Never place database credentials in frontend JavaScript.

# 3. Implementation phases

## Phase 1 — Scope and stream validation (Days 1–2)

Confirm station name, station details, authorized stream URL, and whether Icecast is required.

Test the stream in target browsers and record format, HTTPS behaviour and any limitations.

Agree the MVP: station listing/player, API, MySQL stations, admin management; decide whether listener registration/favourites are included in the first release.

Create a Git repository and .gitignore before adding secrets or dependencies.

Exit: requirements and a working test stream are documented.

## Phase 2 — Frontend radio player (Days 3–4)

Build responsive station/player markup and CSS.

Implement play/pause/resume, volume, loading/playing/paused/buffering/error states.

Handle the audio.play() Promise and media events; do not assume autoplay works.

Test valid, invalid and unavailable stream cases.

Exit: the player works independently of the backend.

## Phase 3 — Backend skeleton (Days 5–6)

Install a supported Node.js LTS release and initialize the backend npm project.

Install Express, mysql2, dotenv, a validation approach, and security middleware as needed.

Create app.js/server.js, environment configuration, centralized error handling and /api/health.

Add request logging without sensitive values, JSON body size limits, and appropriate security headers.

Exit: server starts reliably and health endpoint responds.

## Phase 4 — MySQL schema and connectivity (Days 7–8)

Install/start MySQL locally or provision a database.

Create a dedicated database and least-privilege application user.

Write schema.sql for users, stations, program_schedules and favourites with primary/foreign keys and indexes.

Create a connection pool using environment variables; do not hardcode credentials.

Test a database health query and controlled behaviour when MySQL is unavailable.

Exit: schema can be applied reproducibly and API connects to MySQL.

## Phase 5 — Station and schedule APIs (Days 9–10)

Implement GET /api/stations and GET /api/stations/:id.

Implement schedule listing for a station.

Implement admin create/update/activate/deactivate/delete or archive station endpoints.

Implement admin schedule CRUD endpoints.

Validate URLs, required fields, lengths, IDs, and start/end times; use parameterized SQL.

Test success, missing record, invalid input and database failure cases.

Exit: public reads and admin mutations pass API tests.

## Phase 6 — Authentication and authorization (Days 11–13)

Implement registration and login if listener accounts are in scope; otherwise implement the minimum secure admin sign-in.

Hash passwords with bcrypt and never store plaintext passwords.

Choose JWT-in-HttpOnly-cookie or server-side sessions; document expiry, logout and cookie settings.

Add authentication middleware and an admin-role middleware.

Protect every admin endpoint and test that a guest/listener cannot perform admin actions.

Add login rate limiting and safe error responses.

Exit: authentication and role tests pass.

## Phase 7 — Favourites and frontend/API integration (Days 14–16)

Implement authenticated favourite list/add/remove APIs if included in the agreed scope.

Create a small frontend API helper for fetch calls, JSON parsing, errors and credentials handling.

Populate station cards and schedule views from API responses.

Connect login/logout/register forms and display validation feedback.

Connect the admin UI to station and schedule APIs.

Keep stream playback direct from the stream URL; do not route all audio bytes through Express.

Exit: core user journeys work from browser to database.

## Phase 8 — Optional Icecast integration (Days 17–19)

Skip if an existing stream meets the project requirement.

Set up Icecast and compatible source/broadcast software using official setup guidance.

Configure mount point, source credentials, host binding and network access.

Use a listener URL in the station record; do not expose source credentials in frontend code.

Test playback from two devices and document firewall/HTTPS/hosting limitations.

Exit: optional self-hosted stream works from listener devices.

## Phase 9 — Security, integration and regression testing (Days 20–22)

Run all API, database, authorization and player test cases.

Check SQL injection resistance through parameterized queries, input validation, error handling and secrets hygiene.

Check HTTPS, CORS configuration, cookie settings, rate limiting and server logs.

Test desktop/mobile layouts and keyboard accessibility.

Test API behaviour with MySQL stopped and with invalid stream URLs.

Fix defects and rerun failed tests.

Exit: mandatory tests pass or deviations are documented.

## Phase 10 — Deployment and documentation (Days 23–25)

Deploy the frontend and backend to compatible hosting, or prepare a reproducible local demo.

Provision MySQL securely and apply schema/migrations.

Set production environment variables and HTTPS; do not commit .env.

Verify frontend-to-API origin settings and the deployed stream URL.

Document setup, database initialization, admin bootstrap procedure, API endpoints, tests and known limitations.

Prepare demo data and a short demonstration script.

Exit: another developer can set up, run and test the project from the README.

# 4. MySQL schema plan

Use the following logical relationships. Exact SQL types and deletion rules should be finalized in schema.sql.

| Table | Key fields and constraints |
| --- | --- |
| users | id primary key; name; email unique; password_hash; role enum/check (listener/admin); created_at. |
| stations | id primary key; name; description; genre; stream_url; artwork_url nullable; is_active; timestamps. |
| program_schedules | id primary key; station_id foreign key; title; description; start_time; end_time; is_published; index on station_id and time. |
| favourites | user_id and station_id foreign keys; composite primary key or unique constraint on both; created_at. |

# 5. API implementation order

| Order | Endpoint group | What to verify |
| --- | --- | --- |
| 1 | GET /api/health | Server availability; optionally report database readiness separately. |
| 2 | GET /api/stations, GET /api/stations/:id | Active station listing, detail, 404 handling. |
| 3 | GET /api/stations/:id/schedules | Published schedules and date ordering. |
| 4 | POST /api/auth/register, POST /api/auth/login, POST /api/auth/logout, GET /api/auth/me | Password hashing, validation, cookie/session handling and safe profile output. |
| 5 | GET/POST/DELETE /api/favourites | Authenticated user ownership and duplicate prevention. |
| 6 | POST/PUT/PATCH/DELETE /api/admin/stations | Admin-only station management and validation. |
| 7 | POST/PUT/DELETE /api/admin/...schedules | Admin-only schedule management and valid time ranges. |

# 6. Testing plan

| Area | Tests |
| --- | --- |
| Frontend/player | Play, pause, resume, volume, buffering, invalid stream, retry, responsive layout, keyboard access. |
| API | Expected status codes, JSON shape, invalid input, missing IDs, duplicate email, conflict cases. |
| Database | Schema setup, foreign keys, uniqueness, persistence after restart, connection failure handling. |
| Authentication | Valid/invalid login, logout, expired/absent session, protected endpoint access. |
| Authorization | Guest and listener denied admin mutations; admin allowed. |
| Security | Parameterized SQL, password hashing, .env ignored by Git, rate limits, safe error messages. |
| Integration | Frontend reads from API; admin writes persist to MySQL; favourites are scoped to signed-in user. |
| Optional streaming | Icecast source connection and two-device playback. |
| Deployment | HTTPS, CORS/cookies, environment variables, database connectivity and stream reachability. |

# 7. Risk and troubleshooting guide

| Issue | Check |
| --- | --- |
| API cannot connect to MySQL | MySQL service, host/port, database/user privileges, .env values and connection pool errors. |
| CORS errors | Frontend origin, backend CORS allowlist, credentials option and cookie SameSite/Secure configuration. |
| Login succeeds but later requests are unauthorized | Cookie path/domain, credentials included in fetch, expiry, secret consistency and auth middleware. |
| Admin page hidden but API accessible | Authorization is missing on server; add and test admin middleware on every admin route. |
| Audio fails after deployment | HTTPS mixed content, stream codec, redirect, provider availability and browser network console. |
| Works locally but not remotely | Host binding, firewall, port exposure, database network access and deployment environment variables. |

# 8. Definition of done

Player features work with a valid authorized stream.

Express REST API and MySQL schema run from documented setup instructions.

Station and schedule data persist in MySQL.

Authentication and admin authorization are implemented and tested for the agreed scope.

Favourites work if included in the agreed MVP.

Input validation, parameterized SQL, password hashing and secret handling are in place.

Responsive/accessibility checks and API/integration tests are recorded.

Deployment, database setup, API documentation and known limitations are included in README.

Optional Icecast is demonstrated only if that phase was selected.

# 9. Suggested demo sequence

Open the station listing loaded from the backend.

Open a station and play the live stream; adjust volume and pause/resume.

Show a schedule loaded from MySQL.

Sign in and add/remove a favourite if implemented.

Sign in as administrator and create/update a station or schedule.

Show that changes persist after refreshing the page.

Show a controlled validation or stream-error case.

Show Icecast on a second device if optional streaming was implemented.

# 10. Scope control recommendation

For a manageable internship project, first complete station catalogue + player + Express API + MySQL + secure admin login and station CRUD. Add listener registration, favourites and schedules next if time permits. Keep Icecast optional until the rest is stable.